## Sheet1
Week | Day | Task | Developer Responsible
Week 1: Oct 21 - Oct 27 | Day 1-2 | Project Setup | All
Week 1: Oct 21 - Oct 27 | Day 3-4 | Raw Material (Requisition, Base Material, etc.) | Dev 1 & 2
Week 1: Oct 21 - Oct 27 | Day 5-7 | Purchase (Stock Mgmt, Stock Receive, etc.) | Dev 3 & 4
Week 1: Oct 21 - Oct 27 | Day 5-7 | Opening Balance Count, Finished Goods Report | Dev 4
Week 1: Oct 21 - Oct 27 | Day 6-7 | Complete database schema | All
Week 2: Oct 28 - Nov 3 | Day 1-2 | Sales Return | Dev 1
Week 2: Oct 28 - Nov 3 | Day 3-5 | Delivery Status (VAT, Tax) | Dev 2
Week 2: Oct 28 - Nov 3 | Day 6-7 | Financial Accounts (like Tally) | Dev 3
Week 2: Oct 28 - Nov 3 | Day 6-7 | Accounting tables | Dev 4
Week 2: Oct 28 - Nov 3 | Day 6-7 | Integration with Purchase | All
Week 3: Nov 4 - Nov 10 | Day 1-3 | HRM (Dept, Shift Mgmt) | Dev 1
Week 3: Nov 4 - Nov 10 | Day 4-5 | Petty Cash Management | Dev 3
Week 3: Nov 4 - Nov 10 | Day 6-7 | Line Management | Dev 4
Week 3: Nov 4 - Nov 10 | Day 6-7 | Start Testing | Dev 2 & 3
Week 3: Nov 4 - Nov 10 | Day 6-7 | Begin bug fixing | All
Week 4: Nov 11 - Nov 17 | Day 1-4 | Complete Line Management | Dev 1 & 4
Week 4: Nov 11 - Nov 17 | Day 5-7 | Continue Testing | All
Week 4: Nov 11 - Nov 17 | Day 5-7 | Debugging | All
Week 4: Nov 11 - Nov 17 | Day 5-7 | Final Testing | All
Week 4: Nov 11 - Nov 17 | Day 5-7 | Polish UI/UX | All
Week 5: Nov 18 - Nov 25 | Day 1-4 | Final Testing | All
Week 5: Nov 18 - Nov 25 | Day 1-4 | Bug Fixing | All
Week 5: Nov 18 - Nov 25 | Day 5-7 | Deployment | All
Week 5: Nov 18 - Nov 25 | Day 5-7 | Final Adjustments | All
Week 5: Nov 18 - Nov 25 | Day 5-7 | Project Handover | All